# Replit Prompt — Per-Category Production Capacity (auto-seeded, user-overridable, global)

Replace the single global “Daily capacity (pcs) = 21,335” with a per-category capacity table that is auto-calculated from demonstrated throughput, user-overridable, defined once globally on the Production Planning → Data page, and consumed by every module (weekly release, corrective re-plan, monitoring, warnings).

## 1. Why (two defects in the current model)

- 21,335 is circular, not capacity. It is 576,037 (the plan) ÷ 27 working days — the rate required to hit the plan. Checking the plan against a number derived from the plan proves nothing. Capacity must be measured from what the plant has actually produced.

- Pieces are not fungible across categories. Categories run on different moulds/machines. Cocks Standard averages ~14,034 pcs/day; Cabinet ~77. Being ahead on Cocks creates zero Ball Cock capacity. With one shared pool, the levelling engine will defer an urgent Ball Cock item because “the plant is full” while the Ball Cock line is idle. Capacity must be constrained per category.

## 2. Auto-seeded capacity (the engine)

Source: actual daily output per category — PTMT ANUJ → Production (pieces), mapped to the 7 categories via item_master, over a trailing window (default: last 90 days; configurable). Count only days that category actually produced (a zero day is a scheduling choice, not a capacity limit).

Per category compute and display:

mean_per_day   = mean(daily output)
p90_per_day    = 90th percentile of daily output      <-- DEFAULT capacity
best_day       = max(daily output)
days_observed  = count of producing days

- Suggested capacity = p90_per_day — a sustainable stretch (the plant hits it 1 day in 10), not a one-off best day. mean under-states capability; best_day is not repeatable.

- Recompute on auto-sync (production data is live), so capacity tracks real capability over time.

Seed values from current actuals (Jun + Jul 2026) — the app should reproduce these:

| Category | Mean/day | p90 (suggested) | Best day | Plan needs/day |
| --- | --- | --- | --- | --- |
| Cocks Standard | 14,034 | 17,449 | 19,880 | 14,527 |
| Cocks Premium | 871 | 1,242 | 2,419 | 518 |
| Faucets & Jetsprays & Shower | 1,565 | 2,431 | 3,561 | 2,343 |
| Accessorise | 1,318 | 2,940 | 4,808 | 1,132 |
| Cistern & Seat Cover | 831 | 1,050 | 1,320 | 970 |
| Cabinet | 77 | 147 | 219 | 37 |
| Ball Cock | 3,900 | 6,567 | 17,592 | 1,808 |

(Insight the table must surface: Cocks Standard is the bottleneck — needs 14,527/day against 17,449 demonstrated. Ball Cock has huge headroom — needs 1,808, has hit 17,592. A global number hides both.)

## 3. Override model (identical pattern to the buffer multipliers)

| Column | Who sets it | Behaviour |
| --- | --- | --- |
| Suggested capacity/day | engine | p90 of demonstrated daily output. Always visible, never overwritten. |
| Override capacity/day | user | Blank by default. Type to override that category. |
| Applied capacity/day | derived | IF(Override blank, Suggested, Override) — all modules use this. |

Clearing an override snaps back to the suggestion. Also expose an editable working-days/week (default 6) and shifts (2 × 12 h) — used for the weekly conversion.

weekly_capacity(category) = applied_capacity_per_day × working_days_in_that_week

## 4. Where it lives (global, single source of truth)

Put the table on Production Planning → Data page, section “Production Capacity (pcs/day by category)”, alongside the buffer multipliers. It is global: set once, consumed everywhere.

Remove the per-page “Daily capacity (pcs)” input from the Weekly Corrective Re-Plan screen (and anywhere else it appears). Those screens read the global Applied capacity and simply display it read-only (with a link back to the Data page). One number, one place.

Columns to show per category: Suggested · Override · Applied · Mean · p90 · Best day · Days observed · Plan needs/day · Headroom (= Applied − plan needs/day, RAG: red if negative, amber < 10%, green otherwise).

## 5. Levelling engine — constrain PER CATEGORY

Everywhere capacity is used (weekly release levelling, corrective re-plan, feasibility warnings), the fill must be per category, against that category’s own capacity — never a shared plant pool:

for each remaining week w:
    for each category c:
        cap = applied_capacity[c] × working_days(w)
        take that category's released items, sorted by urgency (lowest cover first)
        fill up to cap;  overflow spills to week w+1 (same category)
    plant_week_load = Σ category loads   # reporting only, NOT a constraint

- Never let surplus capacity in one category absorb another’s overflow.

- CAPACITY_OVERLOAD fires per category (show the ×, e.g. “Cocks Standard W1 = 3.6× capacity”).

- UNFULFILLABLE_THIS_MONTH is computed per category against that category’s remaining capacity.

- Plant-total capacity may be reported (Σ of applied), but must never be used as the constraint.

## 6. Acceptance criteria

- Capacity is computed from PTMT ANUJ actual daily output (per category, trailing window), not derived from the plan. The circular plan ÷ 27 value is gone.

- Per-category table reproduces the seed figures in §2 (e.g. Cocks Standard p90 ≈ 17,449; Ball Cock ≈ 6,567; Cabinet ≈ 147).

- Three-column override works (Suggested / Override / Applied); clearing an override restores the suggestion; Applied is what every module consumes.

- The table lives globally on the Production Planning Data page; the Corrective Re-Plan page no longer has its own capacity input and shows the global value read-only.

- Levelling is per-category: an urgent Ball Cock item is never deferred because Cocks Standard is full; overloads and unfulfillable quantities are reported per category.

- Headroom column flags the bottleneck (Cocks Standard tight, Ball Cock ample) and recomputes as capacity or plan changes.

- Capacity refreshes on auto-sync as new production data arrives; low-observation categories (e.g. Cabinet, few producing days) are flagged “thin data — review” rather than trusted blindly.