# Replit Prompt — PTMT Plant-Level Production Performance Dashboard (Pieces)

Build the Plant-Level tier of the PTMT production-monitoring app. Its single purpose: make sure the plant hits its monthly Production Plan (PP) by tracking actual daily output against plan in real time and driving corrective action before the month is lost. Everything here is in pieces (NOS) — the same unit as the plan. The Machine-Level tier (kg, per-machine, from Report-5) is a separate module built later; do not mix the two.

This is a classic, proven production-control / schedule-attainment system: rate-based targets, cumulative plan-vs-actual burn-up, projected month-end, catch-up planning, exception alerts, and recovery recommendations.

## 1. Scope

- In scope (now): Plant-Level dashboard, velocity/pace-to-target, attainment & variance, warnings, recommendations, historical trend — all in pieces.

- Out of scope (later, separate tier): Machine-Level (utilisation, run-hours, kg output, rejection by machine) from the Report-5 workbooks. Keep the code and navigation cleanly separable (own routes/components/services).

## 2. Tech stack (Replit-native — same as the other apps)

React + Vite · Express (Node) · Postgres · googleapis (service account) · exceljs / Puppeteer for export. All KPIs recomputed in code; never trust a stored %; never fabricate a 0 — unresolved data shows “needs review.”

## 3. Data sources & IDs

### 3.1 Actual daily production — PTMT ANUJ → Production tab (the one continuous source, in pieces)

- File ID: 1AGmksx4gn6w0Wb9EF__yAV5v89IyAfX_f75ouW2c7Yw · tab gid 1175972414 (Production).

- Columns: Date · Code · Colour · Qty (pcs) · Group. One row per item×colour produced on a date.

- This log spans all months — read it once and filter by date range for any month/day. (Each monthly master’s P-DATA “Production” block is merely a date-filtered IMPORTRANGE of this same tab, e.g. WHERE Date ≥ 2026-07-01 AND < 2026-07-31 — so go to the source, don’t scrape 30 sheets.)

- Do not use the Report-5 machine workbooks here — those are kg/machine and belong to the Machine tier.

### 3.2 Monthly target (the PP) — per month

- Current month: read the target from the planning app (per item & per category: Max = Production Plan, Min = Min Production; totals Max 576,037 / Min 301,918 for July).

- Historical months: read each month’s master workbook SUMMARY for that month’s plan. Monthly master IDs:

| Month | File ID |
| --- | --- |
| Jul 2026 | 1xxYYRdjrVcob3a_eIU7K4RRCzXkl50KMngJ5I8T7xuk |
| Jun 2026 | 170xrcWDdTMvTLSJyCw3yGBWxqOOSfZkesGWunqKr8Rw |
| May 2026 | 1uDsowSmqu8J6NSAPS2AoJBKamkzATQqdtYPONJ7VQAc |
| Mar 2026 | 1wi9FQAHkJG5rksk9WravDJ6Rtuw_Ks3LNcTvQSylERU |
| Jun 2025 | 1mkaiBnYszdIgADd-uBul__tbjGthpHVmDelfjLK1cM0 |

Older masters exist back to 2022 (Jul’22, Sep’22, Nov’22, Dec’22, Jan/Feb/Mar/Apr/May’23, …) and can be registered the same way if deeper history is wanted; the very old ones may store production differently, so validate before trusting. Apr 2026 was not located in the shared drive — ask the user for its ID if that month is needed. Keep the month→ID map in a Postgres sources table so new months are added by config.

### 3.3 Item → category master

- Load from the seeded item_master (category · item_code · colour) so each produced item rolls up to one of the 7 categories and to the PTMT total.

### 3.4 Calendar & shift model

- 27 working days for July (6-day week, Sundays off); editable per month. 2 shifts × 12 h = 24 production hours/day. Weekly = Daily × 6; Daily = Monthly ÷ working-days; Per-shift = Daily ÷ 2. Track working days elapsed (E) and remaining (Rem = WD − E) from the last data date.

## 4. Data model (all in pieces)

- Actuals: from PTMT ANUJ Production → aggregate Qty by date, by item (code×colour), by category (via item_master), and plant total. Cumulative-to-date and per-day series.

- Targets: monthly plan → derive daily / weekly / per-shift and cumulative required (required-per-day × working-days-elapsed).

- Join actual vs target at plant, category, and item grain, per day and cumulative.

## 5. Plant-Level pages (detailed — this is the core)

### 5.1 Production Control Board (landing / daily huddle)

The one-screen “are we winning?” board for the daily production meeting: - Month progress: working day E of WD; % of month elapsed. - Plant headline: Target (month), Produced-to-date, Attainment % (cumulative), Projected month-end & projected attainment %, Ahead/Behind (days & pcs). - Today: today’s target (pcs), today’s actual, gap, and whether today closed or widened the gap. - Per-category strip: each category’s cumulative attainment %, RAG-coded, sorted worst-first. - Exceptions count by severity; top 3 recommended actions.

### 5.2 Velocity / Pace-to-Target

The “will we make it” analysis: - Burn-up (S-curve): cumulative Required line vs cumulative Actual, with the projected line extended to month-end. Plant and per-category. - Rate table: Required/day, Actual/day (to date), Pace index (actual-cum ÷ required-cum), Projected month-end, Projected attainment %, Days ahead/behind, Catch-up/day (= (Target − Produced) ÷ Rem) and Catch-up vs plan (= catch-up/day ÷ required/day). - Linearity index: are they producing evenly or back-loading? (std-dev / mean of daily output; flag heavy back-loading as risk). - Feasibility check: compare catch-up/day to demonstrated best-day and to 2-shift capacity; flag when recovery needs > capacity.

### 5.3 Attainment & Variance

- Plan vs Actual at plant, category, and item — pcs and %. Cumulative and daily.

- Variance Pareto: the vital-few items/categories driving the shortfall (80/20), ranked by pcs behind — so effort goes where it moves PP.

- Mix check: producing the right items? Flag items with actual ≫ plan (over-production) while others sit at 0 (under-production) — a mix/sequencing problem even if plant total looks fine.

### 5.4 Warnings & Alerts (plant-level schema — §6)

Severity-sorted, RAG-coded, each with the triggering value, threshold, scope, and source.

### 5.5 Recommendations (recovery engine — §7)

Prioritised, quantified corrective actions.

### 5.6 Trend & Benchmarking

- Month-over-month final attainment %, average daily rate, linearity, and best/worst categories, using the registered historical masters. Establishes the plant’s baseline and whether control is improving.

## 6. Core formulas (pieces; recompute in code)

WD = working days, E = elapsed, Rem = WD − E. - Produced-to-date = Σ Qty (PTMT ANUJ Production, date ≤ snapshot). - Required/day = Target ÷ WD · Required-cum = Required/day × E. - Attainment % (cum) = Produced-to-date ÷ Required-cum. - Attainment % (month) = Produced-to-date ÷ Target. - Actual/day = Produced-to-date ÷ E · Projected month-end = Actual/day × WD · Projected attainment % = Projected ÷ Target. - Days ahead/behind = (Produced-to-date − Required-cum) ÷ Required/day. - Catch-up/day = (Target − Produced-to-date) ÷ Rem · Catch-up vs plan = Catch-up/day ÷ Required/day. - Linearity = 1 − (stdev(daily) ÷ mean(daily)) — lower = lumpier/back-loaded. - RAG bands (attainment / pace): green ≥ 95% · amber 85–95% · red < 85% (tune per plant); projected-miss and infeasible-catch-up escalate to Critical.

Use Max (Production Plan) as the primary target and Min as the floor; report attainment against both (hitting Min = must; hitting Max = goal).

## 7. Warning schema (editable thresholds)

| Code | Condition | Default | Severity |
| --- | --- | --- | --- |
| BEHIND_PACE | Pace index below | < 90% High · < 80% Critical | High/Critical |
| WILL_MISS_PP | Projected attainment below 100% | by gap size | Medium→Critical |
| CATCHUP_INFEASIBLE | Catch-up/day ÷ required/day above, or > best-day capacity | > 1.3× | Critical |
| BELOW_MIN_TRAJECTORY | Projected < Min floor | — | Critical |
| CATEGORY_LAGGING | A category’s attainment far below plant avg | gap > 15 pts | High |
| BACKLOADING | Linearity below (output concentrated late) | index < 0.6 | Medium |
| MIX_IMBALANCE | Items at 0 output while others over-produce | plan>0 & actual=0 for high-plan item | High |
| NO_PRODUCTION | High-plan item, 0 output for N days | N = 3 | High |
| TODAY_MISSED | Today’s actual < today’s target | — | Medium |
| DATA_STALE | No production rows for the latest working day | — | Info (“needs review”) |

Severity colours: Critical red · High orange · Medium amber · Info grey. Never raise a warning from a fabricated 0 — suppress and mark “needs review.”

## 8. Recommendations engine (priority order, quantified)

- Behind pace (plant/category) → add overtime / extra shift; show catch-up/day and extra shift-hours = extra pcs ÷ demonstrated pcs-per-hour.

- Reallocate capacity → category ahead (proj > 110%) → category behind (proj < 90%): move effort, with the surplus/shortfall pcs.

- Resequence to plan → when MIX_IMBALANCE: prioritise the zero-output high-plan items now; list them by pcs behind.

- Focus the vital few → the Pareto items that close ~80% of the gap; produce these first.

- Protect the floor → if BELOW_MIN_TRAJECTORY, escalate: the Min PP is at risk, not just the stretch target.

- Infeasible recovery → if catch-up exceeds capacity, flag for re-planning / added capacity (a management decision, not just overtime), early enough to act.

Each recommendation shows the driving numbers, the suggested quantity, and the category/item scope.

## 9. Acceptance criteria

- Plant and Machine are two clearly separate tiers; only Plant is built now, in pieces, reading PTMT ANUJ Production for actuals (never Report-5).

- Selecting a month pulls that month’s daily production (pcs) by date-filtering PTMT ANUJ Production, rolls it to plant/category/item via item_master, and compares to the month’s target.

- All KPIs in §6 compute and reconcile to a hand-check on a sample day (e.g., July day-5 produced-to-date vs required-cum).

- Velocity burn-up, attainment Pareto, warnings (§7), and recommendations (§8) all render with editable thresholds; no fabricated 0s.

- Historical months load from the registered master IDs for trend/benchmarking; month→ID map is config-driven in Postgres.

- Export (Excel + PDF) of the Control Board, Velocity, and Warnings for the daily meeting.