# Replit Prompt — Weekly Corrective Re-Plan (rolling revision + capacity levelling)

Add a Weekly Corrective Plan: at the end of each week (or on demand), the app re-plans the remaining weeks of the month using what has actually happened — production achieved, new orders received, stock consumed — and issues a revised, capacity-feasible release so the floor can take corrective action while the month can still be saved.

## 0. Why this is needed (a real, measured problem)

The cover-based weekly release is a priority ranking, not a feasible schedule:

|  | pcs |
| --- | --- |
| Week-1 release (July) | 463,012 (81% of the month) |
| Plant capacity per week (6 days × 21,335/day) | ~128,010 |
| Actual run-rate (Jul 1–6) | 23,079/day ≈ 138,000/week |

Week 1 demands 3.6× a week of capacity. The plant is running fine (23,079/day, above the 21,335 plan average) yet will still look catastrophically “behind” in W1, and that phantom gap snowballs into every later week. So the corrective engine must level to capacity — not merely roll the shortfall forward.

## 1. Trigger & inputs

- Run: automatically at each week boundary, plus a “Re-plan now” button. Always uses live auto-synced data.

- Inputs (all live):

  - Original weekly release (W1–W4 per item) from the planning engine.

  - Actual production to date per item ← PTMT ANUJ (Production), by date → week.

  - New orders received this month ← Order Sheet 26-27 (<month> tab) + live pending — orders dated after the plan was generated.

  - Current pending and stock.

  - Capacity: working days remaining × daily capacity (default 21,335/day; editable; optionally use the demonstrated rate — trailing 7-day average).

## 2. Revised requirement (per item)

Step 1 — Refresh position.

stock_now      = stock_open + produced_to_date − dispatched_to_date
pending_now    = current open pending (includes NEW orders this month)
produced_to_date = Σ actual production this month (per item)

Step 2 — Recompute the requirement (same formula, fresh inputs):

buffer_req_rev  = Avg-3-Month-Sale × Applied multiplier
plan_rev        = (buffer_req_rev − stock_now) + pending_now + pending_last_month_outstanding
remaining_to_produce = max( plan_rev − produced_to_date , 0 )

Step 3 — Attribute the change (this is the corrective insight — show it explicitly):

Δ_new_orders   = pending_now − pending_at_plan_time        (demand added mid-month)
Δ_production   = produced_to_date                          (demand satisfied)
Δ_net          = plan_rev − plan_original

Every item gets: original plan · produced · new orders · revised remaining · Δ and its cause.

New items enter the plan if a fresh order makes plan_rev > 0 where it was 0.

## 3. Re-release across the remaining weeks (with capacity levelling)

- Re-score urgency: cover_now = stock_now ÷ Avg-3-Month-Sale; re-assign each item’s remaining_to_produce to a week via the per-category bands (items already replenished naturally fall to later weeks — the loop is self-correcting).

- Level to capacity — the key step:

  - Compute each remaining week’s capacity = working days in week × daily capacity.

  - Sort that week’s released items by urgency (lowest cover first), then fill to capacity.

  - Overflow spills into the next week (and so on). Anything that cannot fit inside the month is flagged UNFULFILLABLE_THIS_MONTH with the quantity and the items — an explicit, visible decision, never a silent overrun.

- Carryover from missed weeks is folded into remaining_to_produce, so nothing is lost — but it is re-prioritised, not blindly stacked.

- Output a revised W_k…W4 schedule that is achievable, plus the deferred/unfulfillable list.

## 4. The Corrective Plan page

- Header: week just closed · produced vs released · lag (pcs) · new orders received · revised month-end outlook.

- Variance attribution card: the gap decomposed into production shortfall vs new demand vs capacity infeasibility — so management knows why the plan moved.

- Revised release table (per item): Original W · Produced · New orders · Remaining · New week · Priority (cover) · status (on-plan / carried over / deferred / unfulfillable).

- Category rollup of revised W1–W4 vs capacity (bar per week, capacity line overlaid).

- Corrective actions (quantified): overtime hours needed to clear this week’s revised load; items to prioritise today; items to defer; categories to reallocate capacity toward.

- Excel + PDF export of the revised plan for the floor.

## 5. Warnings

| Code | Condition |
| --- | --- |
| WEEK_LAG | produced < released for the closed week (with pcs and %) |
| CAPACITY_OVERLOAD | a week’s released load > that week’s capacity (show the ×) |
| UNFULFILLABLE_THIS_MONTH | remaining load exceeds remaining capacity in the month |
| NEW_DEMAND_SPIKE | new orders this month materially raise a category’s requirement |
| STOCKOUT_IMMINENT | cover_now ≈ 0 and the item is not in the current week’s release |
| PLAN_DRIFT | revised month total deviates from the original plan beyond a threshold |

## 6. Acceptance criteria

- Re-plan runs at week boundaries and on demand, using live production, orders, stock, pending.

- remaining_to_produce recomputes per item, and the Δ is attributed to production shortfall vs new orders (both shown).

- The revised release is capacity-levelled: no week is scheduled above its capacity; overflow spills forward; anything beyond the month is flagged UNFULFILLABLE_THIS_MONTH (not hidden).

- Reproduces the July diagnostic: W1 release 463,012 vs ~128,010 weekly capacity → CAPACITY_OVERLOAD at 3.6×, with the plant’s actual 23,079/day correctly shown as on-rate, not “behind”.

- Carryover is re-prioritised by fresh cover, not blindly stacked; replenished items correctly drop to later weeks.

- Corrective actions are quantified (pcs/day, overtime hours, defer list) and exportable (Excel + PDF).